## Raging Volcano Legend Of Pompei
Raging Volcano Legend Of Pompeii
Total Estimated Game Effort (Dev + QA)
Complex | Duration (days) | Effort - Dev | Effort - SIT/QA | Effort - GP | Owner | Revised Start Date | Revised End Date | Actual Start Date | Actual End Date | Game status | Delays | Game completion % | Comments
counta
Art Packaging + Mock-Ups + share with Dev |  |  |  |  | Art
Pre-Kickoff |  |  |  |  | Art
Pre Development Processes
Game Understanding / Queries | 2 | 16
Assets Analysis and Verification | 0.5 | 4
WBS Creation | 0.5 | 4
Project Setup | 0.5 | 4
GP Tasks
Game Specification (Approval from client + Share with dev team)
Mock-ups (review + verification + approval)
Info Text
Help Screen
Sound Manifest
Pre-Test (Testers assigned on pre-test will be assigned on the QA TCs, in case of any exception, proper hand over has to be done by the tester who had done the pre-test)
Doc/ Assets Review | 1 |  | 8
Game Understanding | 1.5 |  | 12
Test Plan | 0.25 |  | 2
Test Cases | 1.75 |  | 14
Game cheats | 2 |  | 16
Kick Off | 0.25 | 2
Game Development - Desktop
Game Intro Screen
Game Intro UI and animations | 1 | 8
Base Game – Desktop
Base Game UI Implementation | 2 | 16
Base Game Background animations | 1 | 8
Menu Panel Creation | 0.25 | 2
Pay table | 0
Menu Panel New UI + Functionality | 1 | 8
Button Panel + Playermsg | 1 | 8
External help page(English) | 0.5 | 4
Player Message | 0.5 | 4
Play scatter landing on reel stop [Sound combinations] | 0.5 | 4
Outer grid implementation | 2 | 16
Symbol Ordering [Indexing/ layering] | 1.5 | 12
Mystery Symbols, Jackpot Symbols, Wild Feature[X2, X3] | 2 | 16
Gamble
Gamble feature UI Update and functionality check | 0.5 | 4
Server Integration
Server Integration (Symbol Mapping, reel set update, Verify win, stack values, update Line pattern, Verify HUD handling with client config, Latest wrapper & Platform update) | 2 | 16
Reel set maping and stop reel base on grid | 1 | 8
Free Game selection screen/outro creation
Transition | 1 | 8
Emperor Anticipation | 1 | 8
Free game intro | 1 | 8
Outro | 0.5 | 4
Free Game – Desktop
Free game UI update | 2 | 16
Free game retrigger | 1 | 8
Fire Ball Feature in Base Game
Fire Ball Feature parsing | 0.5 | 4
Reel spinning handling with outer reel area where fire ball symbols starts spinning | 2 | 16
Fire ball symbols handling on reel | 2 | 16
Fire Anticipation handling on reels when Fire ball lands | 0.5 | 4
Fire ball changes to Wild, X2 Wild, X3 Wild as per no. of ball stops on that reel | 2 | 16
Win Presentation on feature winning | 1 | 8
Gem Symbols/ overlay symbol handling
Gem symbols spinning handling | 1 | 8
Gem symbols landing on reels and animation handling | 1 | 8
Jackpot Feature
Jackpot Parsing | 0.5 | 4
Gem symbols landing on reels and full Gem symbol animation on reel | 0.5 | 4
JP feature presentation on winning JP meters | 1 | 8
JP feature presentation on reels after JP meters | 1 | 8
JP outro - Grand/ Major/Minor/Mini | 1 | 8
JP sound integeration | 1 | 8
FireBall Feature In Free Games
| 0.75 | 6
| 0.5 | 4
| 0.75 | 6
Reel Grid Update after conversion animation | 0.75 | 6
Code review & Peer review
Code review fixes | 1 | 8
Peer Review Fixes | 1 | 8
Win presentation sequence
Change Win Presenatation sequence according to Feature play first | 0.5 | 4
Anticipation - 1
Presentation animation | 0.25 | 2
Implementation in Free game | 0.25 | 2
Jackpot
Parse JP won reponse | 0.5 | 4
Show overLay symbols on reel | 1 | 8
Play overlay collection animation | 0.75 | 6
Play overlay collection hide animation | 0.75 | 6
jackpot reel entry transition animation | 0.75 | 6
Jackpot UI | 1 | 8
Jackpot Reel spinning | 2 | 16
Jackpot Presentation/outro banner | 0.75 | 6
Jackpot to Basegame transition | 0.5 | 4
Jackpot retrriger play one more time | 0.75 | 6
jackpot Sounds integration | 0.5 | 4
Sound (Pre - Post)
Load Pre - Post Sound | 0.5 | 4
Base game Sound Integration | 0.5 | 4
Free Game Sound integration | 0.5 | 4
Big Win
Sound | 0.5 | 4
Assets implementation | 0.5 | 4
Feature Play in autoplay/turbo
Handle all the feature in autoplay | 0.75 | 6
Handle all the feature in turbo | 0.75 | 6
JP Notification in Basegame and Freegame
Basegame | 0.25 | 2
Freegame | 0.25 | 2
Code review & Peer review
Code review and code review fixes | 1 | 8
Peer Review Fixes | 1 | 8
QA Sanity 1 (Random Testing without Test Cases) |  |  | 16 |  | QA
QA Sanity 1 fixes and QA verification | 2 | 16
GP review# 1 |  |  |  | 16 | GP
GP Review# 1 Fixing | 2 | 16
Client Review#1 - Desktop
Broken game
Base Game, Free Game & Gamble Broken | 1 | 8
Jackpot | 1.5 | 12
Expanding Reel - Base game | 0.75 | 6
Expanding Reel - Free game | 2 | 16
Gold Panda | 1 | 8
Mobile Client Development
Mobile Client Development (Landscape & Portrait) - Game Intro, Base Game, Free Game, Free Game Intro Outro | 3 | 24
Jackpot | 1 | 8
Expanding Reel - Base game | 1 | 8
Expanding Reel - Free game | 1 | 8
Gold Panda | 1 | 8
Verify on mobile devices | 1 | 8
Peer Review Fixes | 1 | 8
Game History
Game History | 5 | 40
Code review and code review fixes | 1 | 8
Client Review #1 Fixes | 2 | 16
QA Sanity 2 (Random Testing without Test Cases) |  |  | 16 |  | QA
QA Sanity 2 fixes and QA verification | 2 | 16 |  |  | QA + Dev
GP review# 2 - Full game |  |  |  | 16 | GP
GP feedback and fixes | 2 | 16 |  |  | GP + Dev
Client Review#2 - MOBILE |  |  |  |  | GP
Post Loading in Desktop + Mobile | 1 | 8
Optimized asset Integration | 1 | 8
Localization
Localization Implementation (7 lang) | 4 | 32
Help Page Localization | 2 | 16
Localization Review Mobile | 0.5 | 4
Currency Implementation | 0.5 | 4
Client Review#2 Fixes | 1 | 8
QA Sanity 3 (Random Testing without Test Cases) |  |  | 16 |  | QA
QA Sanity 3 fixes and QA verification | 1 | 8 |  |  | QA + Dev
GP review #3 |  |  |  | 16 | GP
GP feedback and fixes | 1 | 8
Client Review#3 - MOBILE + DT
Client Sign-off
-TC 1 Testing -DT + Mobile |  |  | 24 |  | QA
Localization fixing | 1 | 8
TC1 issues fixing | 4 | 32
Client Review# 3 fixes | 1 | 8
TC 2 - QA (Incl. TC1 Verification) |  |  | 16 |  | QA
TC2 issues fixing | 3 | 24
TC 3 - QA (Incl. TC2 Verification) |  |  | 8 |  | QA
TC3 issues fixing | 2 | 16
Beta Release - QA verification and Release